## Read me
Eventtia — Event Budget Template
Free to use and share. From the guide: https://www.eventtia.com/event-budget-template/
How to use this template:
1. Work in the 'Budget' tab. Fill the Estimated column at kickoff for every line item that applies.
2. When a contract or purchase order is signed, fill the Committed column. Committed > Estimated is your early warning.
3. After the event, fill Actual (including extras and overtime). Variance is calculated automatically.
4. If the event has revenue, use the 'Revenue' tab the same way: conservative targets, tier-by-tier tracking.
5. See the 'Worked example' tab for a filled-in 200-person conference budget.
Three rules that keep the budget honest:
- One owner per category. The event owner holds the total and the contingency.
- Update on a schedule (weekly), not on memory.
- Close it out after the event: this year's Actual column is next year's Estimated column.
Delete example rows you don't need; add line items freely — keep the three-column discipline.

## Budget
Event budget
Three columns or it doesn't count: Estimated at kickoff, Committed on signature, Actual after the event.
Line item | Estimated | Committed | Actual | Variance (Est−Act) | Owner / notes
1. Venue
Room hire
Security deposit
Insurance rider
Cleaning
Overtime hours
Parking
Subtotal
2. Catering
Food & beverage (per head × headcount)
Staff meals
Service charges
Corkage
Dietary surcharges
Subtotal
3. AV & production
Sound
Screens & projection
Lighting
Stage build
Streaming equipment
Technicians
Rehearsal time
Overtime
Subtotal
4. Speakers & talent
Speaker fees
Travel
Accommodation
Green room
Subtotal
5. Marketing & promotion
Paid campaigns
Design work
Photography / videography
Printed programs
Subtotal
6. Event technology
Registration & ticketing platform
Event app
Check-in hardware
Badge printing
Wi-Fi upgrade
Payment processing fees (2–4% of revenue)
Subtotal
7. Staffing
Temporary staff
Agency fees
Uniforms
Briefing time
Subtotal
8. Travel & accommodation
Team travel
Room blocks
Ground transport
Subtotal
9. Signage & print
Banners
Wayfinding
Badges & lanyards
Table cards
Subtotal
10. Contingency (10–15%, untouchable until event week)
Contingency reserve
Subtotal
TOTAL

## Revenue
Event revenue
Budget against conservative attendance, not the target. Track per tier, not just the total.
Revenue line | Price | Target qty | Sold / signed | Revenue | Notes
Early-bird tickets
Standard tickets
VIP tickets
Group / team tickets
Sponsorship — headline
Sponsorship — standard packages
Exhibitor fees
Other
TOTAL REVENUE

## Worked example
Worked example — 200-person, one-day corporate conference
Shares matter more than dollars: venue + catering + AV should land between 50% and 60%.
Category | Estimated (USD) | Share
Venue | 12000 | 20%
Catering ($55/head + service) | 13000 | 21%
AV and production | 10000 | 16%
Speakers and talent | 6000 | 10%
Marketing and promotion | 5000 | 8%
Event technology | 4000 | 7%
Staffing | 3000 | 5%
Travel and accommodation | 2500 | 4%
Signage and print | 1500 | 2%
Contingency (12%) | 7000 | 11%
TOTAL | 64000 | 100%