## Read me
Eventtia — Event Planning Template
Free to use and share. From the guide: https://www.eventtia.com/event-planning-template/
One document, seven sections. This is the working file your team returns to every week between kickoff and doors-open.
How to use it:
1. Fill '1. Overview' first — especially the event owner. One name, final say.
2. Write objectives with numbers attached ('2. Objectives'). No number, no objective.
3. Set the immovable dates in '3. Timeline', working backwards from event day.
4. '4. Budget' is a summary view — the full three-column budget lives in the companion Event Budget Template:
https://www.eventtia.com/event-budget-template/
5. One name per row in '5. Team & roles'. Committees plan; owners ship.
6. '6. Marketing & registration' — the page goes live before promotion starts.
7. '7. Run of show' — fifteen-minute resolution, an owner on every line. Print it on event day.
Review the whole file weekly: same day, fifteen minutes, whole team.

## 1. Overview
Overview
One line matters more than the rest: the event owner.
Field | Your answer
Event name
Format | In-person / virtual / hybrid
Date and time | Include the time zone
Venue / platform
Target audience | Who this event is for
Expected attendance
Event owner | One name. Final say.

## 2. Objectives
Objectives & success metrics
If you can't attach a number, it's not an objective — it's a hope.
Type | Objective | Metric / number | Measured how
Primary | e.g. Generate 150 qualified leads for the sales team
Supporting | e.g. 80% attendance rate from registrations
Supporting | e.g. NPS above 40 in the post-event survey
Supporting

## 3. Timeline
Timeline
Milestones beat task lists. Set the immovable dates first, then fill the gaps.
When | Milestone | Owner | Status
T–12 weeks | Objectives approved, budget signed off, venue/platform booked
T–10 weeks | Registration page live, speakers confirmed
T–8 weeks | Marketing campaign launches
T–6 weeks | Catering, AV, and vendor contracts signed
T–4 weeks | Agenda locked, registration reminder wave
T–2 weeks | Run-of-show drafted, staff briefing scheduled
T–1 week | Final headcount to vendors, badges and signage printed
T–0 | Event day — run-of-show governs
T+1 week | Survey sent, debrief held, report written

## 4. Budget summary
Budget summary
Summary view only — track line items in the companion Event Budget Template (eventtia.com/event-budget-template).
Category | Estimated | Committed | Actual
Venue
Catering
AV & production
Speakers & talent
Marketing & promotion
Event technology
Staffing
Travel & accommodation
Signage & print
Contingency (10–15%)
TOTAL

## 5. Team & roles
Team & roles
Every row has exactly one name. Small event? One person holds several rows.
Role | Owner (one name) | Covers
Event owner |  | Final decisions, budget, stakeholders
Logistics lead |  | Venue, vendors, catering, AV
Marketing lead |  | Promotion, email, social, registration numbers
Content lead |  | Agenda, speakers, session materials
Registration & check-in lead |  | Registration flow, attendee data, on-site check-in

## 6. Marketing & registration
Marketing & registration
The registration page goes live before any promotion starts.
Field | Your answer
Registration opens | Date
Registration target | Plan for 25–40% no-show on free events
Channels | Email list, LinkedIn, partners, paid
Wave 1 — launch | T–8 weeks
Wave 2 — mid-cycle | T–4 weeks
Wave 3 — last call | T–1 week
Registration platform | Forms, confirmations, reminders, attendance data in one system

## 7. Run of show
Run of show
Fifteen-minute resolution, one owner per line. Print it — Wi-Fi fails at the worst moments.
Time | What happens | Owner | Notes
07:00 | Staff arrival, AV check | Logistics
08:00 | Check-in opens | Registration lead | Two lanes minimum
09:00 | Doors open, welcome | Event owner